## Migration
Task | Description | Findings/observations | Timeline | Status | Comments
Initial Assessment | 1. Assess the current Confluent Platform environment and its components. 2. Identify Kafka topics, connectors, schemas, ksql, and security configurations. | o. Availability Zone: 3 o. Number of Brokers: 6, with 2 broker in each AZ o. Number of Zookeeper: 3, with 1 in each AZ o. Number of Connect Instances: 3 Connectors: Oracle CDC AWS Snowflake AWS Kinesis IBM MQ JDBC Connector o. Number of Schema Registry Instances: 3 with one registry in each AZ o. Number of REST Proxy Instances: 1 o Number of ksqlDB Instances: 1. o. Topics and its configurations can be found from repository o. Users and RBACs
Confluent Cloud Setup | Configure the network settings to allow communication between on-prem and Confluent Cloud.
Security Configuration | 1. Define your security requirements for Confluent Cloud, including authentication mechanisms (e.g., API keys, SASL, OAuth 2.0). 2. Plan and configure access control lists (ACLs) for Confluent Cloud
Configure Azure AD | Configure azure AD with confluent cloud for authentication and authorization.
Key management system | Integrate key management system where customers can bring their own key or use default lkey
Data Migration | Migrate data from Kafka topics in your on-premises Confluent Platform. Also validate data.
Connector Migration | 1. List down all the connectors currently used. 2. Check for compatiability with confluent cloud. 3. Configure the connectors. 4. Ensure that source and sink connectors work correctly.
Update DNS and Configurations | Update DNS records and configurations to point to Confluent Cloud for client applications
New customer onboarding | Create a terraform script as template using which new customers can do self service to onboard.
Create template config for existing customers | This is needed for existing customers to have complete selfservice
Integrate Observability tool | Integrate Observability tool to monitor the cluster.
Application testing | Test few customers
Integration Testing | Do a complete end to end testing.
Performance testing | Test how the new environment performs.
Running the 2 environment in parallel | Once the Confluent Cloud environment is fully set up, we should establish a parallel operation with the on-premises Confluent Platform. This involves configuring MirrorMaker to replicate data from the Confluent Platform to the Confluent Cloud. During this parallel operation, we will closely monitor the performance and behavior of both environments for a duration of one month. It's important to note that any operational notifications or alerts should only be generated from the Confluent Platform and not from the Confluent Cloud. This approach ensures a gradual transition while allowing us to thoroughly assess the cloud environment's stability and performance.
Decommission Resources | Once we have tested the env in parallel, we should start decommisioning the resoutces in confluent platform.