## Goal of project
Goal of Migration | Status | Comments
Have the self service platform.
Decrease cost
Increase profit
Reduce operation time and cost
Have the platform ISO 2027 certified |  | Optional

## Process
Tasks | Sub Task | Description | start Date | End Date | Progress | Comment
Create Project in Jira |  | Start a project in Jira and create all the tasks | 22nd November | 23rd November | Done
Project resources and confluent help |  |  | 22nd November | 30th November
Decide what help we need from confluent.
how many internal resources are required.
How to order a Kafka streaming service
| Do we use serviceNow or Sailpoint for placing the order. |  |  |  |  | This request is required for billing.
| Customer should pre order groups with RBACs, so that users inside the group will have access to confluent resource as per the group policy. |  |  |  |  | This is because, IAM team doesnot allow to create groups via terraform.
| Customer should create a branch of the main code in Git, make their changes are create a pull request. |  |  |  |  | We should make sure, customers dont have access to other customers configurations.
Customer should go through guradrails documents, so that, they have information about the process
Create Jira ticket, if customer need help regarding integration.

## Development
Tasks | Sub Task | Description | start Date | End Date | Progress | Comment
Decide on Architecture
| Decide on cluster type and model | Decide if we are using shared model or dedicted model
| multi region support |  |  |  |  | This will be required for diaster recovery
Internet as carrier
| 3 env dev, test and prod |  |  |  |  | What should the environment be called
how will client connect, broker and Rest proxy
Kafka connect
KSQL
Schema registry
Cluster linking
Cluster replication
Diaster recovery
Create trust between Confluent cloud and Azure AD
| Establish connectivity between Confluent cloud and Azure AD |  |  |  |  | We have to white list Confluetn cloud public ip, so that it can access Azure AD
| Get Azure details which are required to set it as Identity provider in Confluent cloud |  |  |  |  | Connect with IAM team to get the details
Infrastructure as code for | [5 empty] | Code should be modularised and configurable.
Store backend config and sensitive data inside azure key valut?
Environment and cluster
| User and access |  |  |  |  | User should come from Azure AD
Topics with RBACs
KSQLDB
Schema registry and stream governance
| Networks |  |  |  |  | If we are using dedicated cluster.
Integrate Azure ad with terrafrom script
Implement RBACs for access
| If we are using Scania certificate to encrypt data, where will the certificate be stored. |  |  |  |  | We should sue azure key vault to store the certs.
Confluent portal access to end user | We should use SSO with RBACs to give modular access to every customers |  |  |  |  | OAuth and AAD Enable SAML SSO and MFA Appl oauth Appl let’s encrypt Group mapping Claims and Pools (AuthZ) Just-in-time user provisioning (If ready) Self Service AD (Scope, role, claims)
Self service
User should have access to git repoistory and should make changes and create a pull request.
Create CI/CD pipeline
Kafka connect on-prem
Install K8s cluster where all connectors will be deployed
Template to deploy connectors
There should be connectivity between on-prem and confluent cloud via K8s
Documentation
We should have clear and precise documentation for customer on-boarding
We should also have videos showing customer on boarding
Have sample templates for most common use cases

## Migration
Tasks | Sub Task | Description | start Date | End Date | Progress | Comment
Inform Customers
| Inform customers about migration plan and share a tentative timeline. |  | 1st December | 1st December
| Find out customers who are using mtls and inform them about requiremtn to change auth method from mtls to oauth |  | 1st December | 1st December
Migration
Cluster linking between stockholm platform to Confluent cloud.
For one to many integration, we should use mirror maker to migrate 1 consumer at a time.
Cluster linking between EU and China with the help of replication.

## Monitoring and billing
Tasks | Sub Task | Description | start Date | End Date | Progress | Comment
Monitoring
Use data dog to monitor cluster and application.
See how we can provide access to customer to access their topic metrics in datadog
Billing
Decide on billing model
Decide how cost will be shared

## Operations
Tasks | Sub Task | Description | start Date | End Date | Progress | Comment
Cluster maintainance
Reduce the cluster size of Confluent platform, once the cloud environment is ready to onboard customers
Decide how many respurces are needed to maintain this environment
Cluster maintainance | Define SLA for tickets.

## Diaster recovery
Tasks | Sub Task | Description | start Date | End Date | Progress | Comment
Diaster recovery
Multi region deployment
Take regular backups.
Do a DR dry run to see, how fast can we recover from disater.

## NFR
Tasks | Sub Task | Description | start Date | End Date | Progress | Comment
NFR
Availability
Scalability
Performance
Reliability and Durability
Security
Compliance